## EQC-LATEST-STAGE-REPORT-04-21-2
Date | Project | Inspector | Eqc Type | Stage | EQC | Location Variable | Status | Approver | Action By | Action Timestamp | Time Zone | Team | Total EQC Stages | Fail Stages | % Fail | URL
2026-04-16 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Rooftop-Walkway Installation Vietnam | Walkway Installation(Láº¯p Ä‘áº·t lá»‘i Ä‘i) | Devyt Tobacco Phase2/Walkway Installation | Devyt Tobacco Phase2/Walkway Installation | PASS | - | - | 2026-04-17 01:20 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/408431
2026-04-16 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Rooftop-PV Module Installation Vietnam | PV Module Installation(CÃ i Ä‘áº·t mÃ´-Ä‘un PV) | Devyt Tobacco Phase2/PV Module Installation | Devyt Tobacco Phase2/PV Module Installation | PASS | - | - | 2026-04-17 01:19 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/408422
2026-04-16 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Rooftop-AL Rail Installation Vietnam | AL Rail Installation(CÃ i Ä‘áº·t Ä‘Æ°á»ng sáº¯t AL) | Devyt Tobacco Phase2/Walkway Installation | Devyt Tobacco Phase2/Walkway Installation | PASS | - | - | 2026-04-17 01:16 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/399642
2026-04-16 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Rooftop-Life Line Installation Vietnam | Life Line Installation(Láº¯p Ä‘áº·t Life Line) | Devyt Tobacco Phase2/Life Line Installation | Devyt Tobacco Phase2/Life Line Installation | PASS | - | - | 2026-04-17 01:15 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/408418
2026-04-16 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Electrical-LT Panel Erection Vietnam | LT Panel Erection(Láº¯p Ä‘áº·t táº¥m LT) | Devyt Tobacco Phase2/LT Pannel Erection | Devyt Tobacco Phase2/LT Pannel Erection | PASS | - | - | 2026-04-17 01:07 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/408416
2026-04-16 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | PV Module-Cable Dressing & Earthing Vietnam | RFI - PV Module Cable Dressing & Earthing(BÄƒng cÃ¡p mÃ´-Ä‘un PV & ná»‘i Ä‘áº¥t) | Devyt Tobacco Phase2/PV Module Dressing & Earth | Devyt Tobacco Phase2/PV Module Dressing & Earth | REJECTED | - | Tri Dinh | 2026-04-16 10:22 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/408425
2026-04-16 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Electrical-LT Panel Cable Termination Vietnam | RFI - LT Panel Cable Termination(Äáº§u cÃ¡p báº£ng LT) | Devyt Tobacco Phase2/LT Panel Cable Termination | Devyt Tobacco Phase2/LT Panel Cable Termination | PASS | - | - | 2026-04-16 10:19 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/408413
2026-04-10 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/AC Cable | Devyt Tobacco Phase2/AC Cable | PASS | - | - | 2026-04-10 12:35 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/404330
2026-04-10 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/PV Connectors | Devyt Tobacco Phase2/PV Connectors | PASS | - | - | 2026-04-10 12:34 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/404342
2026-04-10 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/DC Cable | Devyt Tobacco Phase2/DC Cable | PASS | - | - | 2026-04-10 12:33 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/404329
2026-04-04 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/Lifeline | Devyt Tobacco Phase2/Lifeline | PASS | - | - | 2026-04-04 02:06 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/392263
2026-04-04 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/Earthing Materials | Devyt Tobacco Phase2/Earthing Materials | PASS | - | - | 2026-04-04 02:05 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/398002
2026-04-04 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/Inverter | Devyt Tobacco Phase2/Inverter | PASS | - | - | 2026-04-04 02:04 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/399625
2026-04-04 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Rooftop-AL Rail Installation Vietnam | AL Rail Installation(CÃ i Ä‘áº·t Ä‘Æ°á»ng sáº¯t AL) | Devyt Tobacco Phase2/AL Rail Installation | Devyt Tobacco Phase2/AL Rail Installation | PASS | - | - | 2026-04-04 02:04 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/399611
2026-04-04 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/ACCB pannel | Devyt Tobacco Phase2/ACCB pannel | PASS | - | - | 2026-04-04 02:03 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/399610
2026-04-04 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/PV Module | Devyt Tobacco Phase2/PV Module | PASS | - | - | 2026-04-04 02:01 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/402049
2026-03-11 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/Handrail | Devyt Tobacco Phase2/Handrail | PASS | - | - | 2026-03-11 11:59 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/392771
2026-03-09 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/Cable Tray | Devyt Tobacco Phase2/Cable Tray | PASS | - | - | 2026-03-10 12:35 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/392593
2026-03-09 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/AL Rail | Devyt Tobacco Phase2/AL Rail | PASS | - | - | 2026-03-10 12:34 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/392269
2026-03-09 | 737.1KWp Devyt Tobacco Phase-2, Vietnam | Tran Dac Duy | Incoming Material Inspection Report (IMIR) Vietnam | Incoming Material Inspection (Kiá»ƒm tra váº­t liá»‡u Ä‘áº¿n) | Devyt Tobacco Phase2/Walkway | Devyt Tobacco Phase2/Walkway | PASS | - | - | 2026-03-10 12:32 | Asia/Vientiane | HFE Roof Top Vietnam |  |  |  | https://app.digiqc.com/projects/2401/eqc/392255
[13 empty] | 20 | 0 | 0